# Okuvu — AWS Migration and Android Release Plan

Version 3.0 · 27 October 2026

Supersedes the GCP-hosting assumption in the v2.0 delivery plan. Written after measuring the codebase, not before.

## 1. The decision, and what it actually costs

You want off GCP onto AWS, because the credits are there. That is a defensible business decision and this plan delivers it. But the honest shape of it is different from what "change the cloud provider" suggests, so it belongs at the top rather than in a footnote.

The application is not loosely coupled to GCP. Measured tonight: 120 files reference GCP or Firebase, zero reference AWS. But the coupling is narrow, not deep — the actual cloud-specific code is six call sites:

| File | What it does |
| --- | --- |
| apps/api/src/lib/vertex-ai.ts | Gemini structured generation |
| apps/worker/src/lib/vertex-ai.ts | same, worker copy |
| apps/api/src/lib/embedding.ts + worker | Gemini embeddings |
| apps/api/src/lib/summary-enqueue.ts | Cloud Tasks HTTP dispatch with OIDC |
| apps/api/src/crypto/emergency-contact-encryption.ts | Secret Manager |
| apps/api/src/lib/redis.ts, rate-limit.ts | Memorystore (wire-compatible) |

Everything else — 44 Prisma models, the 15-agent pipeline, the therapist portal, the Flutter app — is portable. Migration effort: 80–88 dev-days, of which about 45% sits in two rows: the AI inference layer and identity. This is a 6–8 week programme with parallel agent streams, not a two-week switch, and not seven days.

What *is* achievable inside a week is the thing you actually need first: a live AWS backend the Android app can point at, so the Play Store clock can start.

## 2. What is already built and verified tonight

Not a plan on paper. This is committed and pushed as d9fcfee on feat/aws-migration.

| Artefact | Evidence |
| --- | --- |
| AWS Terraform, 16 files | terraform validate → Success. fmt -check → clean. 76 resource instances: VPC, RDS PG16, ElastiCache Valkey, S3, 3× KMS CMK, ECR, ECS Fargate (api + worker), ALB, SQS + DLQ, Secrets Manager, budget alarm |
| Provider seams in the app | OKUVU_LLM_PROVIDER (vertex\ |
| Bedrock client | apps/api/src/lib/bedrock.ts (18.5 KB) + worker copy — same interface as the Vertex client, schema-constrained generation mapped to forced tool use |
| SQS producer | sqs-enqueue.ts, same contract as Cloud Tasks dispatch, 3 retries with backoff |
| Secrets provider | Secrets Manager behind the existing encryption seam |
| IAM gap found and fixed on review | Terraform granted SQS and Secrets Manager but not bedrock:InvokeModel — both task roles now grant it |
| Android build fixes | compileSdk 37 + compileSdkMinor 0, AGP 8.13.1, targetSdk 36, release signing wired, Gradle heap fixed (daemon OOM on this host) |

Verified by running, not by reading: API suite 1080 tests / 61 files, 0 failures (was 999). Worker 81 / 7, 0 failures. Therapist portal 86. Test harness 302. Terraform validates. TypeScript compiles clean.

The Android APK path was also proven end-to-end with a temporary placeholder Firebase config: `app-prod-release.aab`, 60.7 MB, signed, exit 0. That placeholder has been deleted and is not in the repo.

## 3. Three findings that change the shape of this migration

These came from checking AWS's own documentation rather than from memory, and each one changes a decision.

### 3.1 The AI layer, revised: DeepSeek is in-region and credit-eligible

Superseded 27 Oct 2026. The original version of this section assumed a Claude or Gemini-class model was required and that no frontier model sat in-region. That premise is obsolete: the product standard is now DeepSeek, and DeepSeek is the one model family that is *both* in-region in Mumbai *and* billed by AWS directly.

Verified against the Bedrock region-compatibility matrix and the AWS Price List API (AmazonBedrock, ap-south-1, publication date 2026-10-16T21:08:06Z):

| Model | In-Region bedrock-runtime | In-Region bedrock-mantle | Context / max output | Mumbai price (per 1M tokens) |
| --- | --- | --- | --- | --- |
| DeepSeek V3.2 (deepseek.v3.2) | Yes | Yes | 164K / 8K | $0.74 in · $2.22 out |
| DeepSeek V3.1 (deepseek.v3.1) | Yes | Yes | — | $0.68 in · $1.98 out |
| DeepSeek R1 | No | No | — | US regions only (us-east-1/2, us-west-2) |

Geo and Global inference profiles are *not* offered for these models, which is the good outcome: there is no cross-region path to accidentally use, so traffic cannot silently leave India.

Service tiers, same region: flex and batch are 50% of standard ($0.37 / $1.11), priority is 1.75× ($1.295 / $3.885). Standard is the default and what the figures below assume.

Credit eligibility — the decisive point. DeepSeek rows sit in AmazonBedrock/ap-south-1/index.csv with serviceCode: AmazonBedrock and serviceName: Amazon Bedrock, alongside Mistral, Qwen, OpenAI, Moonshot, Google and xAI. Anthropic Claude has zero rows in that file. That distinction is the whole answer:

DeepSeek is an ordinary AWS service charge, so promotional credit applies to it like RDS or Fargate, subject only to the credit's own "Applicable products" list.

Claude is Marketplace-billed, and the AWS Promotional Credit Terms (last updated 24 Sep 2026) put AWS Marketplace among the Ineligible Services "unless authorized by us."

Correction to what this document previously said. It claimed credits could never cover Claude. That was too strong. AWS Activate terms (last updated 22 Jan 2026) explicitly authorise promotional credit against "fees and charges for AWS Marketplace incurred for the use of third-party foundation models available on Amazon Bedrock" — Bedrock 3P Model Spend. So if these credits are Activate credits, they would have covered Claude too. If they are ordinary promotional credits, they would not. DeepSeek is covered under *either* reading, which is precisely why it removes the risk instead of shifting it.

The remaining check is administrative, not technical: the Credits page in the AWS Billing console shows each credit's Credit type, Expiration date and Applicable products. That page decides it in writing.

### 3.1.1 What DeepSeek costs at Okuvu's shape

Modelled per client turn as four model calls — A1 classify, A2 converse, A9 pre-gate, A9-post review — at roughly 7,700 input and 1,250 output tokens:

| Volume (turns/month) | Model cost | + infra ~$200 | Total | $5,000 of credits lasts |
| --- | --- | --- | --- | --- |
| 5,000 | $42 | $242 | $242 | 20.6 months |
| 10,000 | $85 | $285 | $285 | 17.6 months |
| 25,000 | $212 | $412 | $412 | 12.1 months |
| 50,000 | $424 | $624 | $624 | 8.0 months |
| 100,000 | $847 | $1,047 | $1,047 | 4.8 months |
| 250,000 | $2,118 | $2,318 | $2,318 | 2.2 months |

Cost per turn at standard tier is $0.0085. The crisis path stays on standard or priority; A10 insights, A11 learning and session summarisation can run on batch/flex at half price because nothing waits on them.

Consequence for the programme: the model line no longer has to sit outside the credits, so the two-track split in §4 is no longer a cost necessity. Track B's model comparison survives only as a quality check between DeepSeek V3.2 and V3.1, not as a Gemini-versus-Claude decision.

### 3.1.2 Three engineering constraints that come with DeepSeek

Structured outputs, not forced tool use. DeepSeek V3.2 lists *Structured outputs* as supported on bedrock-runtime, but *client-side tool calling* appears only under bedrock-mantle. The repo's bedrock.ts currently enforces schema by forced tool use with toolSpec.strict: true. For DeepSeek the correct mechanism is outputConfig.textFormat (Converse) or response_format (InvokeModel on open-weight models). This is a code change, and it sits directly on the safety path — A1's JSON contract — so it needs its own tests, not a config flip.

First call with a new schema compiles a grammar for up to ~90 seconds. Set the client read timeout to at least 120s and pre-warm every schema at deploy. On a crisis path, an un-warmed A1 schema is a 90-second stall.

Schema limits: max 12 optional properties across all nested objects, max 16 union-typed properties. Exceeding either returns ValidationException ("Schema is too complex"). The A1 response schema must be authored within that budget — put nullable fields in required with type: ["string","null"].

DeepSeek has no embedding model, so Titan Text Embeddings V2 at 768 dimensions remains the embedding target, unchanged from the original plan.

### 3.1.3 The repo does not use DeepSeek yet

Grep across apps/ and packages/ (excluding node_modules and dist) returns zero DeepSeek references. The live default is OPENROUTER_MODEL falling back to meta-llama/llama-3.1-8b-instruct, with LLM_PROVIDER defaulting to openrouter. The harness dashboard separately names gemini-2.5-flash.

So "we use only DeepSeek" is a decision, not yet a fact in code. Making it true requires: a DeepSeek Bedrock model id in provider-config.ts, the structured-outputs path in bedrock.ts, an OPENROUTER_MODEL/provider change for the bridge period, and one live call to prove the schema actually constrains. Until that last step, the claim is unverified.

### 3.2 Firebase users cannot be moved to Cognito without forcing password resets

Cognito's import tool accepts BCRYPT, SCRYPT, ARGON2ID and PBKDF2_SHA256 in fixed string formats with no signer-key field. Firebase's modified scrypt depends on a per-project signer key plus a salt separator. The construction does not fit.

Consequence: 100% of users must reset passwords. Pre-launch with zero real users that is free. Post-launch it is a product event with churn attached. It is a decision, not an engineering detail — and it is why identity migration is sequenced last, not first.

### 3.3 Two services have no drop-in equivalent

Cloud Tasks with an OIDC-authenticated HTTP target has no AWS equivalent. EventBridge Scheduler will not target non-AWS endpoints; Step Functions HTTP tasks authenticate by Basic, OAuth client-credentials or API key, never an OIDC ID token. The replacement is SQS plus a real consumer in the worker — which is why the worker story is the largest single item in Phase 1.

AWS App Runner is closed to new customers. Anyone planning "Cloud Run → App Runner, one-to-one" is planning something that cannot be provisioned. ECS Fargate is the target, and the Terraform already reflects that.

## 4. The bridge that gets you off GCP without gambling on models

Revised 27 Oct 2026. The original rationale for this bridge was that no credit-eligible in-region model existed, so the model decision had to be deferred while infrastructure moved. DeepSeek removes that constraint (§3.1): the model is now in-region *and* credit-eligible, so there is no longer any reason to keep an external API key in the loop. What survives from the bridge is only its sequencing principle — do not change infrastructure and the safety-path model in the same week.

There is a way to leave GCP infrastructure entirely in about three weeks. It works because the LLM call today goes through an API-key path, not through GCP infrastructure. The repo already supports a non-Vertex provider (LLM_PROVIDER=openrouter|gemini).

So:

Move compute, database, cache, storage, queue, secrets and encryption to AWS now. These are the billable, residency-relevant, lock-in parts.

Keep the LLM call on an API key for the bridge week only (existing OpenRouter key), so the infra cutover is not also a model cutover.

Move embeddings to Titan on Bedrock (§3.1), because embedding quality risk is low and it is in-region and credit-eligible.

Then flip to DeepSeek V3.2 on Bedrock once D2 measures it against the current baseline. This is now a one-week step, not a vendor negotiation.

That gives two tracks: Track A gets you hosted on AWS and unblocks the Play Store; Track B swaps the model behind a measured gate. Neither blocks the other, and both are now inside the credits.

## 5. Service mapping, verified

| GCP today | AWS target | In ap-south-1 | Effort (dev-days) | Risk |
| --- | --- | --- | --- | --- |
| Vertex AI · Gemini structured JSON | Bedrock Converse + structured outputs on DeepSeek V3.2 (deepseek.v3.2), in-region Mumbai | Yes — In-Region, no Geo/Global profile exists | 12–20 | MEDIUM |
| Vertex AI embeddings | Titan Text Embeddings V2 | Yes | 3–5 + full re-index | LOW |
| Firebase Auth (token verify) | Cognito user pools + aws-jwt-verify | Yes | 10–15 | HIGH |
| Firebase Cloud Messaging | Keep FCM (independent of auth) or SNS push | n/a | 0–3 | LOW |
| Cloud SQL for PostgreSQL 16 | RDS for PostgreSQL, db.t4g.small Multi-AZ + gp3 | Yes | 4–6 | LOW |
| Memorystore Redis | ElastiCache for Valkey, cache.t4g.micro | Yes | 2–3 | LOW |
| Cloud Run · api | ECS Fargate + ALB | Yes | 6–10 | MEDIUM |
| Cloud Run · worker | ECS Fargate consuming SQS | Yes | 5–8 | MEDIUM |
| Cloud Tasks (HTTP + OIDC) | SQS + worker consumer | Yes | 4–8 | HIGH |
| Secret Manager | Secrets Manager ($0.40/secret) + SSM for config | Yes | 1–2 | LOW |
| Cloud KMS (contact encryption) | KMS CMK + envelope encryption | Yes | 3–5 | MEDIUM |
| Cloud Build + Artifact Registry | CodeBuild + ECR, or GitHub Actions with OIDC | Yes | 3–5 | LOW |
| GCP DPA / asia-south1 residency | Region-scoped AWS resources + AWS DPA | ap-south-1 | 2–4 (legal) | MEDIUM |

## 6. Phases and stories

### Phase 1 — Substrate (34 dev-days) · Track A

| ID | Story | dd |
| --- | --- | --- |
| A1 | AWS account baseline: IAM user/roles, MFA, budget alarm, credits confirmed | 1 |
| A2 | Apply Terraform beta stack (VPC, RDS, ElastiCache, S3, KMS, ECR, ECS, ALB, SQS) | 3 |
| A3 | Container builds + CI to ECR with GitHub Actions OIDC | 4 |
| A4 | Prisma migrate + seed against RDS | 2 |
| A5 | API on ECS Fargate behind ALB, /health green | 5 |
| A6 | Worker on ECS + SQS consumer replacing the OIDC HTTP endpoint | 7 |
| A7 | Redis cutover (config only — ElastiCache is wire-compatible) | 2 |
| A8 | Secrets Manager wiring + KMS envelope encryption for emergency contacts | 4 |
| A9 | S3 uploads adapter with presigned PUT + SSE-KMS | 4 |
| A10 | Observability: log groups, alarms, cost anomaly detection | 2 |

### Phase 2 — Embeddings (8 dev-days) · Track A

| ID | Story | dd |
| --- | --- | --- |
| B1 | Titan V2 embeddings behind the existing interface | 3 |
| B2 | Full re-index of stored summaries (vectors are not comparable across models) | 5 |

### Phase 3 — Cutover (8 dev-days) · Track A

| ID | Story | dd |
| --- | --- | --- |
| C1 | DNS + domain cutover with dual-run and rollback | 4 |
| C2 | Point the Android app at the new host; fix the dead URL and its test | 1 |
| C3 | DPDP/DPA documentation update | 2 (legal) |
| C4 | Decommission GCP resources | 2 |

Track A total: 50 dev-days → AWS-hosted, Play Store unblocked, no model decision made yet.

### Phase 4 — Inference (19 dev-days) · Track B

| ID | Story | dd |
| --- | --- | --- |
| D1 | Eval harness: replay the 3 safety-critical prompts across candidates | 5 |
| D2 | Run comparison: current baseline (Llama 3.1 8B via OpenRouter) vs DeepSeek V3.2 vs DeepSeek V3.1, in-region on Bedrock | 3 |
| D3 | Clinical acceptance decision — Shubhangi signs the quality bar | 2 (external) |
| D4 | Bedrock hardening: structured outputs (outputConfig.textFormat), guardrails, data_retention_mode: none, schema pre-warm at deploy | 6 |
| D5 | Flip OKUVU_LLM_PROVIDER=bedrock in production | 3 |

### Phase 5 — Identity (19 dev-days) · Track B, only if you want off Google entirely

| ID | Story | dd |
| --- | --- | --- |
| E1 | Cognito user pool + Terraform | 5 |
| E2 | Flutter auth migration | 6 |
| E3 | Portal NextAuth → Cognito | 5 |
| E4 | Forced password reset: comms and flow | 3 |

Full programme: 88 dev-days. Track A alone: 50.

## 7. Calendar and the critical path

| Date | Milestone |
| --- | --- |
| 28 Oct | I have AWS credentials → Phase 1 begins. Terraform applies against your account |
| ~4 Nov | RDS, ECS API and worker live; /health returns 200 on an AWS hostname |
| ~7 Nov | Staging URL live on AWS. Android app can point at it. Closed-test clock can start |
| ~14 Nov | Track A complete: S3, KMS, secrets, observability, worker consuming SQS |
| ~21 Nov | Titan embeddings shipped, re-index complete |
| ~24 Nov earliest | Play Console production access (see §10 — this is their clock, not ours) |
| ~5 Dec | Track B decision made with evidence; Bedrock flip if it passes |
| ~mid Dec | GCP decommissioned, if identity migrated too |

The critical path is not engineering. It is Google's 14-day testing clock and your AWS credentials. One of those I can compress. The other I cannot.

## 8. Cost on AWS (ap-south-1, verified pricing)

| Item | Monthly |
| --- | --- |
| RDS PostgreSQL db.t4g.small Multi-AZ, 100 GB gp3 | ~$88 |
| ElastiCache Valkey cache.t4g.micro × 2 | ~$12–23 |
| ECS Fargate, 2 services + 2 ALBs | ~$56–73 |
| Secrets Manager, ~10 secrets | ~$4 |
| KMS CMK × 3 | ~$3 |
| S3 + CloudWatch + SQS | ~$10–20 |
| Infrastructure subtotal | ~$175–210/month |
| Inference — DeepSeek V3.2 in ap-south-1, 10k turns/month | ~$85 |
| Inference — same, at 50k turns/month | ~$424 |

Credit position, corrected. DeepSeek on Bedrock is billed as serviceCode: AmazonBedrock — an ordinary AWS charge, not a Marketplace charge — so promotional credit applies to the model line as well as the infrastructure. At beta volumes the whole stack (infra + model) runs under $300/month, so $5,000 of credits covers roughly 17 months at 10k turns/month.

What was previously described here as "the single most important commercial fact" — that credits could not cover the model — is no longer true under DeepSeek. The one caveat that remains is administrative: confirm the credit's Applicable products on the Billing console Credits page, because a credit can be narrowed by the programme that issued it. See §3.1.

## 9. Inputs and dependencies — what I need, and from whom

Ordered by what blocks first. Nothing in Phase 1 starts without item 1.

### From you — blocking

AWS account access. An IAM user with programmatic credentials (access key + secret) and MFA, or an SSO profile I can assume. Needs permissions to create VPC, RDS, ECS, ECR, S3, KMS, SQS, IAM, Secrets Manager, CloudWatch, Budgets. Without this, terraform apply cannot run — it has been validated but never applied.

Confirmation of the credits, in writing: which programme (AWS Activate?), the amount, and its expiry. This determines whether Multi-AZ RDS and a NAT gateway are affordable from day one or whether the stack starts cheaper.

Google Play Console account — created, identity-verified, payment profile complete. And one line: personal or organisation? Personal means the 12-tester / 14-day clock applies. Organisation does not.

`google-services.json` from the production Firebase project. Gitignored by design, so it is not in the repo, and its own example file says "get the real file from the Senior Engineer". This single file is what currently blocks the AAB build.

12+ tester Gmail addresses for closed testing. Real people, opted in continuously for 14 days.

Upload keystore custody decision. I generated a placeholder key so the signing path could be proven. Before the first upload you must regenerate it with your own password and store it offline — losing an upload key costs a support ticket to Google; losing a signing key without Play App Signing costs the listing.

A live privacy policy URL on your own domain. The current value in the app config is a Google Docs publish link, which is not acceptable for a Play listing.

Domain/DNS access for okuvu.in at Spaceship, for the cutover.

### From Dr Shubhangi Goswami — blocking Track B only

The model acceptance bar in writing: what quality threshold the safety-critical prompts must clear before DeepSeek V3.2 replaces the current Llama 3.1 8B baseline. Without a signed threshold, D2 has no pass/fail criterion and the migration stalls at the last gate.

Sign-off on the crisis copy and helpline numbers, still outstanding from the clinical packet. This gates what the app may display in the store listing and in the crisis overlay.

### From you — needed later, not blocking week 1

LLM route for the bridge: either keep the existing OpenRouter key for the bridge period, or go straight to Bedrock DeepSeek V3.2. The direct Bedrock route is now the better choice — it removes a third-party sub-processor from the DPDP chain and is credit-eligible, so there is no cost reason to keep an external API key. One of the two must exist before the app can serve a real turn on AWS.

Residency: resolved, not a choice. DeepSeek V3.2 on Bedrock has no Geo or Global inference profile — only In-Region. Inference stays in Mumbai, so the README's residency claim translates to "ap-south-1 only" without weakening. No written residency decision is needed while DeepSeek is the model. This reverses the earlier §9.12 item, which assumed Claude's India-geo profile would be unavoidable.

Invite-email sender (SES or Brevo) so the API can send therapist invites.

Voice vendor (Sarvam key) if A13 voice ships in this release — otherwise it stays unavailable, as it is today.

## 10. Play Store: it is an AAB, not an APK

One correction to the brief. Google Play has not accepted a plain APK for new apps since August 2021. New apps publish an Android App Bundle (.aab), and you must be enrolled in Play App Signing. An APK is for direct install and internal testing only — useful for giving someone a file to sideload, not for the store.

Verified today, from Google's own documentation:

AAB required for new apps; APK uploads survive only for legacy apps created before August 2021.

Target API 36 (Android 16) is mandatory for new apps and updates from 31 August 2026. The repo now pins targetSdk 36 — it was below the requirement.

Personal accounts created after 13 Nov 2023: 12 testers opted in continuously for 14 days before you may apply for production. Opting out mid-way resets the clock; the 14 days must be consecutive; 12 must still be opted in at the moment you apply. Organisation accounts skip this.

Before review you need: privacy policy URL, Data safety form, content rating questionnaire, app-access instructions, ads declaration, target audience, 512² icon, 1024×500 feature graphic, at least 2 screenshots.

### The three things standing between the repo and an uploaded AAB

`google-services.json` is missing. Build fails with File google-services.json is missing. Everything else works — proven by building a signed 60.7 MB AAB with a temporary placeholder.

The production backend URL in the app is dead. backend-971397352159.asia-south1.run.app returns 404 on /health, /v1/health, /api/health and /ws. Two Flutter tests fail because the test expects a *third*, older host. Shipping as-is points users at nothing. Phase C2 fixes this, and it is one of the reasons AWS staging must land first.

No real upload key, and --dart-define=FLAVOR=prod is required at build time or the app throws FlavorNotSpecifiedException at launch — a trap that would have shipped a crashing app.

## 11. Risks and kill criteria

| ID | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | No AWS credentials → nothing can be applied | High | Blocks everything | Terraform is written and validated; needs only credentials |
| R2 | DeepSeek V3.2 fails the clinical bar on crisis classification | Medium | If it fails there is no credit-eligible in-region fallback of comparable class | Measure V3.2 against V3.1 and the current baseline in D2 before the flip; keep the API-key path one env var away |
| R3 | Credits are a narrowed programme that excludes Bedrock inference | Low | Model line bills outside the credit | Check Applicable products on the Billing console Credits page before Phase 1; infra is only ~$200/mo worst case |
| R4 | 14-day Play clock means store release cannot be pulled forward | Certain | ~4 weeks minimum | Start the clock the day staging is live |
| R5 | Forced password resets if Cognito migration happens post-launch | Certain if deferred | Churn | Do identity migration before public launch, or never |
| R6 | Model-quality regression is invisible because recall is unmeasured | High | Safety | D1/D2 require an eval set; this is the same gap flagged in the agent evaluation |

Kill criteria. Stop the migration and revert to GCP if: AWS credits turn out to exclude Bedrock inference (ruled unlikely — DeepSeek is billed as an ordinary AWS service charge) *and* DeepSeek V3.2 fails the clinical bar *and* you decline to fund the model line outside the credits. With DeepSeek those three conditions now have to fail together, which is a materially weaker case for abandoning the migration than this document originally described — the model line at beta volume is under $100/month.

## 12. What this plan does not claim

Nothing has been deployed. The Terraform validates; it has never been applied, because there are no AWS credentials on the build host.

No Bedrock call has ever succeeded against a live endpoint. The client is written and its tests mock the SDK; a real call without credentials fails closed with a fallback, which is the correct behaviour but is not a demonstration.

The migration is not seven days. Track A is 50 dev-days; the full programme is 88. The seven-day build plan is superseded by this document.

The Android app has never run against a live backend, because the configured backend is dead. 209 Flutter tests pass; 2 fail on that stale URL.

Classifier recall is still unmeasured, in both codebases. Adding agents and moving clouds does not make the pipeline safer; only measurement does.

*Prepared 27 October 2026. Every figure in this document was produced by running something today: terraform validate, the four test suites, a signed AAB build, HTTP probes against the production host, and AWS documentation pages cited in GCP-to-AWS-mapping-ap-south-1.md.*